## Sheet1
Bug_ID | Test Scenario | Bug Title | Bug Description | Priority | Severity | Bug Assignee | Reported on | Browser | Browser Version | Bug Type | Environment | Component | Enhancement | Images | Reporter Name | URL | Build Number
BUG-001 | (TS_01) Register Functionality | Back Button navigate to wrong page. | Back Button in second 'Get Started with Free Trail' Page is navigating user to 'Login Page' instead of first 'Get Started with Free Trail' Page. | P2 | Minor |  | 2024-12-04 | Opera | 100.0.2345.45 | functional | window 11 |  |  |  | Rachna Maithani | https://vwo.com/free-trial/?utm_medium=website&utm_source=login-page&utm_campaign=mof_eg_loginpage
BUG-002 | (TS_01) Register Functionality | Keyboard key functionality not working for checkbox field. | No keyboard key is working for marking checkbox option. | P1 | Major |  | 2024-12-04 | Google Chrome | 131.0.6778.141 | functional | window 11 |  |  |  | Rachna Maithani | https://vwo.com/free-trial/?utm_medium=website&utm_source=login-page&utm_campaign=mof_eg_loginpage
BUG-003 | (TS_01) Register Functionality | On Page Refresh user is navigating to different Page. | On Page Refresh user is navigating to different page instread of staying at the same page and all data entered in the form clear. | P3 | Minor |  | 2024-12-05 | Google Chrome | 131.0.6778.142 | functional | window 11 |  |  |  | Rachna Maithani | https://vwo.com/free-trial/?utm_medium=website&utm_source=login-page&utm_campaign=mof_eg_loginpage
BUG-004 | (TS_02) Login Functionality | Login Page is supporting in unsupported Browser. | VWO login page is opening in unsupported browsers. | P0 | Major |  | 2024-12-06 | Google Chrome | 131.0.6778.143 | functional | windown 11 |  |  | https://prnt.sc/Qo2nZRICpscS | Rachna Maithani | https://app.vwo.com/#/login
BUG-005 | (TS_02) Login Functionality | invalid username Autofilled | invalid username is automatically filled on selecting the remember me checkbox after trying to sign in. | P2 | Minor |  | 2024-12-06 | Google Chrome | 131.0.6778.144 | functional | window 11 |  |  |  | Rachna Maithani | https://app.vwo.com/#/login
BUG-006 | (TS_03) Forget Password | Reset password link redirecting to wrong page. | when clicking on reset password link after 2 hours user first navigating to Login page then to Forget Password Page. | P2 | Minor |  | 2024-12-09 | Opera mini | 131.0.6778.145 | functional | windown 11 |  |  | https://prnt.sc/PPQ8anmI90en | Rachna Maithani | https://app.vwo.com/#/forgot-password
BUG-007 | (TS_03) Forget Password | vwo logo is not navigating to vwo.com page. | In Login Page vwo logo is not navigating to vwo.com page. | P3 | Minor |  | 2024-12-09 | Google Chrome | 131.0.6778.146 | GUI | windown 11 |  |  |  | Rachna Maithani | https://app.vwo.com/#/forgot-password
BUG-008 | (TS_03) Forget Password | Resetting password for more than once with the same link then the user is not directly to Login page. | After resetting password once . If user try to reset password with the same link then it is navigating to Forget Password Page then to Login Page. | P2 | Minor |  | 2024-12-09 | Google Chrome | 131.0.6778.147 | functional | windown 11 |  |  | https://prnt.sc/2rY627VvyqZd | Rachna Maithani | https://app.vwo.com/#/forgot-password
BUG-009 | (TS_03) Forget Password | vwo logo is not navigating to vwo.com page. | In Forget Password Page vwo logo is not navigating to vwo.com page. | P3 | Minor |  | 2024-12-09 | Google Chrome | 131.0.6778.148 | GUI | windown 11 |  |  |  | Rachna Maithani | https://app.vwo.com/#/forgot-password
Total Opened Bug |  | 9
Total Closed Bug |  | 0
Risk |  | 0
P0 |  | 1
P1 |  | 1
P2 |  | 4
P3 |  | 3
P4 |  | 0